{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["Лист1","Лист2","Лист3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Лист1","index":0,"n_rows":103,"n_cols":5,"rows_kept":103,"cut":false,"hidden":false,"merged":[[38,4,39,4],[71,4,102,4],[36,1,37,1],[1,4,15,4],[16,4,19,4],[20,4,24,4],[29,4,33,4],[34,4,35,4],[25,4,28,4],[36,4,37,4],[40,4,70,4]]}
["№ п/п","Наименование ГРС","Дата проведения работ, ч.","Продолжительность, час."]
[1,"Бриляково","июнь","24ч.","Семеновское ЛПУМГ"]
[2,"Линда","июнь","24ч."]
[3,"Городец","июнь","24ч."]
[4,"Урень","август","24ч."]
[5,"Ковернино","июнь","24ч."]
[6,"Сокольское ","июнь","24ч."]
[7,"Зарубино","июнь","24ч."]
[8,"Боковая","июль","24ч."]
[9,"Чкаловск","июль","24ч."]
[10,"Красные Баки","июль","24ч."]
[11,"Семенов","июнь","24ч."]
[12,"Вершилово","июль","24ч."]
[13,"Пурех","август","24ч."]
[14,"Балахна","июль","24ч."]
[15,"Заволжье","июнь","24ч."]
[16,"Мурзицы","май","24ч.","Сеченовское ЛПУМГ"]
[17,"КЦ Центр-2 (Сеченово)","июнь","24ч."]
[18,"Петряксы","июль","24ч."]
[19,"Большое Болдино","июль","24ч."]
[20,"Гагино","июнь","24ч.","Пильнинское ЛПУМГ"]
[21,"Сергач","июнь","24ч."]
[22,"Уразовка","июль","24ч."]
[23,"Пица","июль","24ч."]
[24,"КС Пильнинская","август","24ч."]
[25,"Подлёсовская п/ф-ка","август","9ч.","ООО \"Ивтрансгазстрой\""]
[26,"Поя","август","9ч."]
[27,"Саваслейка","август","9ч."]
[28,"Ройка","август","9ч."]
[29,"КЦ Центр-2 (Починки)","май","24ч.","Починковское ЛПУМГ"]
[30,"Арзинка","июль","24ч."]
[31,"Починки","июль","24ч."]
[32,"Наруксово","август","24ч."]
[33,"Кочкурово","август","24ч."]
[34,"Арзамас АМЗ","август","14ч.","ООО \"Регионтрансгаз\""]
[35,"Симбухово","август","8ч."]
[36,"Воскресенское ","июнь","4ч.","ГЭПП \"Нижегородоблкоммунэнерго\""]
[37,null,"август","4ч."]
[38,"Сооружение АГРС-10 (Балахнинская п/ф-ка)","август","24ч.","ООО \"Регионгазсервис\""]
[39,"Вязовка","август","24ч."]
[40,"Умай","май","24ч.","Арзамаское ЛПУМГ"]
[41,"Тилинино","май","24ч."]
[42,"Криуша","май","24ч."]
[43,"Берсениха 1,2","май","24ч."]
[44,"Вад","май","24ч."]
[45,"Волчиха","май","24ч."]
[46,"Ардатов","июнь","24ч."]
[47,"Саконы","июнь","24ч."]
[48,"Мухтолово (филиал г. Павлово)","июнь","24ч."]
[49,"Мухтолово (филиал г. Арзамас)","июнь","24ч."]
[50,"Гремячево","июнь","24ч."]
[51,"Кулебаки","июнь","24ч."]
[52,"Протопоповка","июнь","24ч."]
[53,"Перевоз","июнь","24ч."]
[54,"Кузьмин Усад","июнь","24ч."]
[55,"Навашино","июль","24ч."]
[56,"Вознесенское","июль","24ч."]
[57,"Нарышкино","июль","24ч."]
[58,"Кременки","июль","24ч."]
[59,"Дивеево","июль","24ч."]
[60,"Петровка","июль","24ч."]
[61,"Малый Макателем","июль","24ч."]
[62,"Первомайск","июль","24ч."]
[63,"Казаково","август","24ч."]
[64,"Тольский Майдан","август","24ч."]
[65,"Пешелань","август","24ч."]
[66,"Шатки","август","24ч."]
[67,"Лукоянов","август","24ч."]
[68,"Власть Советов","август","24ч."]
[69,"Выкса","август","24ч."]
[70,"Выкса-2","август","24ч."]
[71,"Горький-2","Май-июнь","24ч.","Приокское ЛПУМГ"]
[72,"Горький-3","Май-июнь","24ч."]
[73,"Дзержинск-2","июль","24ч."]
[74,"Вача","июнь","24ч."]
[75,"Княгинино (филиал в г.Сергач)","июнь","24ч."]
[76,"Княгинино (филиал в г.Богородск)","июнь","24ч."]
[77,"Летнево","июнь","24ч."]
[78,"Новогорьковская ТЭЦ","июнь","24ч."]
[79,"Березовский ","июнь","24ч."]
[80,"Богородск","июнь","24ч."]
[81,"Запрудновский","июнь","24ч."]
[82,"Володарск-1","июль","24ч."]
[83,"Володарск-2","июль","24ч."]
[84,"Кремницкое","июль","24ч."]
[85,"КС Лысково","июль","24ч."]
[86,"Воротынец","август","24ч."]
[87,"Ворсма","август","24ч."]
[88,"Вязовка","август","24ч."]
[89,"Ильиногорск","август","48ч."]
[90,"Кудьма","август","24ч."]
[91,"Лысково ","август","24ч."]
[92,"Коробково","июль/август","24ч."]
[93,"Нива ","август","24ч."]
[94,"Павлово","август","24ч."]
[95,"Смолино","август","24ч."]
[96,"Чугуны","август","24ч."]
[97,"Юганец","август","24ч."]
[98,"Белавка","август","24ч."]
[99,"Березовая Пойма","август","24ч."]
[100,"Варганы","август","24ч."]
[101,"Дзержинск-1","август","24ч."]
[102,"Нижегородец","июль","24ч."]

{"sheet":"Лист2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Лист3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}